## Project Timeline
PROJECT TIMELINE
PROJECT TITLE |  | Leaflings |  | COMPANY NAME | [5 empty] | [Company's name]
PROJECT MANAGER |  | [Project Manager's name] |  | DATE | [5 empty] | 2024-10-02
PHASE |  |  | DETAILS | Q1
|  |  |  | OUT |  |  |  | NOV |  |  |  | DEZ
| PROJECT WEEK: |  |  | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16
1 |  |  | - Requirements + Use Cases | bar: OUT 7 to OUT 14
| Milestone 3 |  | - Database Plan + Data Dictionary | bar: OUT 7 to OUT 14
| Planning and System Design |  | - Architecture + Diagrams | bar: OUT 7 to OUT 14
- Product Backlog | bar: OUT 7 to OUT 14
- Mockups and Design | bar: OUT 14 to OUT 21
| Milestone 4 |  | - API for Plants and Users | bar: OUT 21 to OUT 28
2 | Backend Implementation |  | - Match-making Algorithm | bar: OUT 28 to NOV 11
- Gamify Features | bar: NOV 4 to NOV 11
- Preparing for next Milestone | bar: NOV 18
| Milestone 5 |  | - Develop Web frontend | bar: NOV 25 to DEZ 2
3 | Frontend Implementation |  | - Develop Mobile Frontend (start) | bar: DEZ 2 to DEZ 9
- Develop Mobile Frontend (finish) | bar: DEZ 9 to DEZ 16